## README
Deliverables Gantt Planner - reference workbook
Import this file into Google Sheets (File > Import > Upload), then paste the sheet URL into the planner's "Connect" dialog.
How to use this file
1. | Keep the tab names exactly as they are: plan, stages, gates-system, gates-hc, mg-hc. They are matched in lowercase and the planner will not find them under any other name.
2. | Replace the sample rows with your own. Nothing else has to be renamed or moved.
3. | Yellow cells are the ones you fill in. This README tab is ignored by the planner - you may delete it once you are comfortable with the format.
4. | Share the Google Sheet with the account running the planner (Editor if you want to drag bars and have the change written back; Viewer is enough for read-only).
Tab | Header row? | What the planner reads
plan | Yes, row 1 | One row per deliverable, from row 2 down. This is the only mandatory tab.
stages | NO | Column A, from row 1: the stage names in the order they should appear top-to-bottom in the chart. Duplicates are ignored.
gates-system | Yes, row 1 | A = gate name, B = date, from row 2. Drawn as a red dashed line.
gates-hc | Yes, row 1 | Same shape. Drawn as a purple dashed line with an H/C badge.
mg-hc | Yes, row 1 | Same shape. Drawn as an orange dotted line with an H/C badge.
capacity | Yes, row 1 | OPTIONAL. A = unit, B = from, C = to, D = FTE. How many people a unit has over a period; rows for one unit add up. Drives the over-capacity warnings and the Capacity view.
baseline | Written by the tool | OPTIONAL. Filled in when you press “Capture baseline”. Freezes the plan so the Drift view can show what moved since.
Columns of the "plan" tab
Column | Header | Meaning
A | Ref | Your own reference. Used as the track ID only when column C is empty; otherwise free text.
B | Title | Shown on the bar. Square brackets are stripped out.
C | Track | THE KEY FIELD. One chart row per distinct value. Deliverables sharing a track stack on the same line, and two that overlap in time are flagged as a collision.
D | Stage | Which band the track belongs to. Fill it on the track's first row only - the other rows inherit it. A track belongs to exactly one stage, so do not spread one track across several stages.
E | Amount | A number. Man-hours when column K is empty, a monetary amount when column K says EUR.
F | Start | A real date. Type N/A (or leave blank) to park a deliverable: the row is then skipped.
G | End | A real date, inclusive. If it is earlier than the start the planner swaps the two.
H | Comment | Free text, shown in the tooltip and in brackets after the title.
I | Owner | Free column, IGNORED by the planner. Yours to use.
J | Status | Free column, IGNORED by the planner. Yours to use.
K | Currency | EUR (or euro / the euro sign) marks a monetary item, drawn in green and totalled separately. Anything else, including blank, means man-hours.
L | Unit | Department or team. Drives the filter chips and the per-unit colour. Blank becomes "Unassigned".
Rules worth knowing
- | Dates: type them as real dates. The planner also reads dd/mm/yyyy and yyyy-mm-dd text, but real dates avoid any ambiguity.
- | A row is only plotted when BOTH dates are readable. Everything else is skipped and reported in the status bar.
- | Effort is spread evenly over the days of a deliverable, which is how the monthly FTE curve and the yearly summary are built.
- | Conversion used by the tool: 1580 h/year = 1 FTE (131.7 h/month). This is a fixed convention in the code, not a cell you can change here.
- | Columns can be moved if you rename the header: the planner recognises, among others, Title/Titre, Track/ID, Stage/Phase, Amount/Montant, Start/Debut, End/Fin, Currency/Devise, Unit/Departement. Leave the layout as-is and you never have to think about it.
- | Adding extra tabs is safe - only the named tabs are read.
- | The planner can edit the plan tab back: drag a bar sideways to reschedule it, drag it onto another track to move it there, double-click an empty spot on a track to create a deliverable, and use the editor to change the title, track, stage, dates, amount, currency, unit and comment.
- | Removing a deliverable from the chart only blanks its two date cells (they become N/A). The row, its title and its amount stay in the sheet, and setting dates again brings it straight back.
Cross-check (recomputed from the plan tab)
These cells mirror what the planner should display. If a figure looks wrong, the data is wrong.
Deliverables listed
Deliverables plotted
Rows skipped (no dates)
Distinct tracks plotted
Total effort (Mh)
Equivalent FTE-years
Total budget (EUR)
Earliest start
Latest end
Sample data is illustrative only - a fictitious product-development programme. Replace it entirely.

## plan
Ref | Title | Track | Stage | Amount | Start | End | Comment | Owner | Status | Currency | Unit
D-001 | Market & customer requirements | TRK-01 | Stage 1 - Concept & Requirements | 320 | 2026-01-05 | 2026-02-27 | Voice-of-customer workshops | A. Martin | Done |  | Program
D-002 | System requirements specification | TRK-01 |  | 480 | 2026-03-02 | 2026-04-30 | Stage left blank: inherited from D-001 | A. Martin | In progress |  | Systems
D-003 | Feasibility & concept trade-off | TRK-02 | Stage 1 - Concept & Requirements | 260 | 2026-01-12 | 2026-03-13 | Three concepts compared | L. Dubois | Done |  | Systems
D-004 | Regulatory & homologation study | TRK-03 | Stage 1 - Concept & Requirements | 18000 | 2026-02-02 | 2026-03-31 | External consultancy, fixed price | C. Nguyen | Done | EUR | Quality
D-005 | Mechanical architecture & CAD | TRK-04 | Stage 2 - Design & Architecture | 960 | 2026-04-06 | 2026-07-31 |  | P. Roy | In progress |  | Mechanical
D-006 | Detailed mechanical drawings | TRK-04 |  | 640 | 2026-08-03 | 2026-10-30 | Follows D-005 on the same track | P. Roy | Not started |  | Mechanical
D-007 | Electronics board design | TRK-05 | Stage 2 - Design & Architecture | 720 | 2026-04-06 | 2026-08-28 | Two board revisions planned | S. Keller | In progress |  | Electronics
D-008 | Prototype PCB manufacturing | TRK-05 |  | 45000 | 2026-09-01 | 2026-10-16 | Supplier quote Q-2291 | S. Keller | Not started | EUR | Purchasing
D-009 | Embedded firmware v1 | TRK-06 | Stage 2 - Design & Architecture | 880 | 2026-05-04 | 2026-09-30 |  | M. Okafor | In progress |  | Software
D-010 | Diagnostics & test software | TRK-07 | Stage 2 - Design & Architecture | 400 | 2026-06-01 | 2026-09-30 |  | M. Okafor | Not started |  | Software
D-011 | Design review documentation pack | TRK-08 | Stage 2 - Design & Architecture | 0 | 2026-07-01 | 2026-07-31 | Zero effort: hidden until the 0-Mh toggle | C. Nguyen | Not started |  | Quality
D-012 | Tooling specification | TRK-09 | Stage 3 - Industrialisation | 300 | 2026-10-01 | 2026-12-18 |  | P. Roy | Not started |  | Mechanical
D-013 | Injection tooling purchase | TRK-09 |  | 128000 | 2027-01-04 | 2027-04-30 | Long-lead item | J. Silva | Not started | EUR | Purchasing
D-014 | Assembly line concept | TRK-10 | Stage 3 - Industrialisation | 540 | 2026-11-02 | 2027-02-26 |  | J. Silva | Not started |  | Mechanical
D-015 | Supplier qualification | TRK-11 | Stage 3 - Industrialisation | 380 | 2026-11-02 | 2027-03-31 | Six suppliers in scope | J. Silva | Not started |  | Purchasing
D-016 | Firmware v2 - production intent | TRK-12 | Stage 3 - Industrialisation | 520 | 2026-11-02 | 2027-03-31 |  | M. Okafor | Not started |  | Software
D-017 | Environmental & EMC test campaign | TRK-13 | Stage 4 - Validation & Qualification | 620 | 2027-03-01 | 2027-06-30 |  | C. Nguyen | Not started |  | Quality
D-018 | External EMC laboratory | TRK-14 | Stage 4 - Validation & Qualification | 34000 | 2027-04-01 | 2027-05-31 | Accredited lab, fixed price | C. Nguyen | Not started | EUR | Quality
D-019 | Durability & life testing | TRK-13 |  | 480 | 2027-07-01 | 2027-09-30 | Follows D-017 on the same track | C. Nguyen | Not started |  | Quality
D-020 | Software validation & release | TRK-15 | Stage 4 - Validation & Qualification | 460 | 2027-04-01 | 2027-07-30 |  | M. Okafor | Not started |  | Software
D-021 | Safety case & certification file | TRK-16 | Stage 4 - Validation & Qualification | 340 | 2027-05-03 | 2027-08-31 |  | L. Dubois | Not started |  | Systems
D-022 | Pilot run & process capability | TRK-17 | Stage 5 - Ramp-up & Closure | 700 | 2027-09-01 | 2027-11-30 | 200 units built | J. Silva | Not started |  | Mechanical
D-023 | Production ramp-up support | TRK-18 | Stage 5 - Ramp-up & Closure | 520 | 2027-10-01 | 2027-12-31 |  | J. Silva | Not started |  | Program
D-024 | Project closure & lessons learned | TRK-17 |  | 120 | 2027-12-01 | 2027-12-23 | Follows D-022 on the same track | A. Martin | Not started |  | Program
D-025 | Spare parts catalogue | TRK-19 | Stage 5 - Ramp-up & Closure | 0 | 2027-11-01 | 2027-12-15 | Zero-effort deliverable | J. Silva | Not started |  | Purchasing
D-026 | Post-launch marketing kit | TRK-20 | Stage 5 - Ramp-up & Closure | 150 | N/A | N/A | Dates not fixed: ignored until both are set | A. Martin | Not started |  | Program
Note on B1: One row per deliverable, from row 2 down. Amber = parked (no usable dates, skipped by the planner). Red = the end date precedes the start date. Green = monetary item (column K = EUR).
Note on C1: Deliverables sharing a track are drawn on the same chart row. Two that overlap in time are flagged as a collision.

## stages
Stage 1 - Concept & Requirements | NO HEADER ROW on this tab: row 1 is already the first stage. The order here is the top-to-bottom order of the bands in the chart. A stage with no deliverable is simply not drawn.
Stage 2 - Design & Architecture
Stage 3 - Industrialisation
Stage 4 - Validation & Qualification
Stage 5 - Ramp-up & Closure
Note on A1: Row 1 is data, not a header. Do not insert a title row above it.

## gates-system
Gate | Date
SR1 - Concept freeze | 2026-04-15 | System review gates - red dashed line. Header row in row 1, one gate per row from row 2. A gate without a name or without a readable date is ignored. Drag a gate tag in the planner (read-only off) and the date is written back here.
SR2 - Design freeze | 2026-10-15
SR3 - Industrialisation gate | 2027-03-15
SR4 - Production release | 2027-10-15

## gates-hc
Gate | Date
HC-R1 - Requirements review | 2026-03-16 | H/C review gates - purple dashed line with an H/C badge. Header row in row 1, one gate per row from row 2. A gate without a name or without a readable date is ignored. Drag a gate tag in the planner (read-only off) and the date is written back here.
HC-R2 - Preliminary design review | 2026-07-15
HC-R3 - Critical design review | 2026-11-16
HC-R4 - Test readiness review | 2027-05-14

## mg-hc
Gate | Date
MG1 - Maturity level 1 | 2026-06-15 | H/C maturity gates - orange dotted line with an H/C badge. Header row in row 1, one gate per row from row 2. A gate without a name or without a readable date is ignored. Drag a gate tag in the planner (read-only off) and the date is written back here.
MG2 - Maturity level 2 | 2026-12-15
MG3 - Maturity level 3 | 2027-06-15
MG4 - Maturity level 4 | 2027-11-15

## capacity
Unit | From | To | FTE
Program | 2026-01-01 | 2027-12-31 | 2.5 | OPTIONAL TAB. How many people each unit actually has, as periods rather than a month grid: a ramp-up is one row, not twelve. Rows for the same unit ADD UP - see Mechanical, which gets half an extra FTE from mid-2026, a contractor. The planner compares this with the effort your plan demands and flags the months where a unit is short. Delete the tab and the feature simply switches off. Only man-hour deliverables create demand: a line in EUR buys an outcome, it does not occupy anyone.
Systems | 2026-01-01 | 2027-12-31 | 2.5
Mechanical | 2026-01-01 | 2027-12-31 | 2.5
Electronics | 2026-01-01 | 2027-12-31 | 1.5
Software | 2026-01-01 | 2027-12-31 | 1.5
Software | 2026-06-01 | 2027-12-31 | 0.5
Quality | 2026-01-01 | 2027-12-31 | 1.5
Purchasing | 2026-01-01 | 2027-12-31 | 1

## baseline
Plan row | Track | Title | Start | End | Amount | Captured at
OPTIONAL TAB, WRITTEN BY THE TOOL - do not fill it in by hand. Press “Capture baseline” in the planner's Drift view and today's dates and amounts are frozen here. From then on every bar shows a hollow ghost where it used to sit, and the Drift view lists what slipped, by how many days, and how much effort was added or removed. Re-capturing overwrites it; clearing empties it. Leave the tab out entirely and the planner just creates it when you first capture.